## Sheet1
| Start Date | End Date | Timeline | Status
OreSat Deployable Antennas | 2018-04-02 | 2018-06-10 |  | Active
Select final designs | 2018-04-02 | 2018-04-06 |  | Active
Refine CAD drawings | 2018-04-02 | 2018-04-20 |  | Upcoming
Design of experiment and testing | 2018-04-06 | 2018-05-07 |  | Upcoming
Final CAD | 2018-04-06 | 2018-05-11 |  | Upcoming
Manufacturing of final design | 2018-04-19 | 2018-05-24 |  | Upcoming
Testing and validation | 2018-05-07 | 2018-06-10 |  | Upcoming
System refinement | 2018-05-14 | 2018-05-25 |  | Upcoming
Helical Antenna
Stress Relaxation
- Talk to Wern / other faculty about importance and possibility of testing (Shiva) | 2018-04-09 | 2018-04-13 |  | Upcoming
RF Testing
- Quarterwave transformer (Glenn / one of us if he's busy?) | 2018-04-09 | 2018-04-13 |  | Complete
- Structural groundplane (Justin) | 2018-04-05 | 2018-04-10 |  | Complete
- New CAD for conical reflectors (Calvin) | 2018-04-08 | 2018-04-09 |  | Upcoming
- 3D Print conical reflectors (John) | 2018-04-09 | 2018-04-11 |  | Complete
Structural Analysis / Tether Development
- Free body diagram of antenna with tethers (Justin, Shiva, Calvin) | 2018-04-09 | 2018-04-11 |  | Upcoming
- Determine optimal number of tethers, desired tension in each, and required spring length / gauge to achieve that | 2018-04-11 | 2018-04-13 |  | Upcoming
- Investigate methods of attaching tethers to spring | 2018-04-11 | 2018-04-20 |  | Upcoming
- Research and select tether material | 2018-04-11 | 2018-04-18 |  | Upcoming
- Incorporate tethers into design of stowed antennas with an eye on keeping them from getting tangled | 2018-04-11 | 2018-04-27 |  | Upcoming
CAD Drawings for the System
- Create basic CAD sketches for helix in compressed and deployed configurations, integrate with structure CAD on Git (Calvin) | 2018-04-08 | 2018-04-11 |  | Upcoming
Drop Tower Testing
- Talk to Weislogel / whoever else about running tests near the end of the term | 2018-04-15 | 2018-04-22 |  | Upcoming
- Design and create fixture to rig the deployment system up to the drop chamber | 2018-04-22 | 2018-05-07 |  | Upcoming
- Record video of the drop, analyze dynamics... | 2018-05-07 | 2018-05-21 |  | Upcoming
- Figure out what (if anything) we can or will do with the results | 2018-04-15 | 2018-05-21 |  | Upcoming
Turnstile Antenna
Prototype Design
- Finish 3D models | 2018-04-09 | 2018-04-20 |  | Upcoming
- Print 3D models/Assemble final prototype | 2018-04-19 | 2018-04-23 |  | Upcoming
- Design eagle cad of pcb for mounting | 2018-04-25 | 2018-04-30 |  | Upcoming
RF Testing
- Test RF for both designs | 2018-04-23 | 2018-04-30 |  | Complete
Protype Manufacturing
- Order machined parts and PCB | 2018-05-01 | 2018-05-04 |  | Complete
- Assemble final prototype | 2018-05-07 | 2018-05-11 |  | Complete
Everybody
Vibration Testing
- Meet with Joel, schedule plan going forward | 2018-04-12 | 2018-04-12 |  | Upcoming
- Decide on scope of testing for capstone project | 2018-04-10 | 2018-04-12 |  | Upcoming
- Delegate vibration testing lead, assign responsibility for passing on to PSAS after graduation | 2018-04-12 | 2018-04-19 |  | Upcoming
- Determine how or whether to approach vibration tests of isolated subsystems (i.e. test both antennas at once on a complete structure, or as separate systems separate from the structure) | 2018-04-12 | 2018-04-21 |  | Upcoming
3D Print satellite mount | 2018-04-15 | 2018-04-30
Manufacture Vibration Holder (Machine shop) | 2018-04-15 | 2018-05-07